## Sheet1
Action back log	Status	Sprint ready
Sprint one
create proposal	In progress	Yes
create bit bucket account	Not started	Yes
link trellor to bitbucket	Not started	Yes
set up new laravel project	Not started	Yes
link bit bucket to slack	Not started	Yes
Back log needing to be add to a sprint
create activity diagrams	Not started	No
create ERD	Not started	No
create user case diagrams	Not started	No
Create personas for staff, student, non-edgehill student	Not started	No
develop tables	Not started	No
migrate tables to mysql	Not started	No
seed data for pathways	Not started	No
create bdd test for creating previous project	Not started	No
create bdd test for delete previous project	Not started	No
create bdd test for edit previous project	Not started	No
create bdd test to create new project	Not started	No
create bdd test to delete new projects	Not started	No
create bdd test to edit new project	Not started	No
create bdd tests for adding stafff	Not started	No
create bdd test for edit staff	Not started	No
create bdd to test permissions	Not started	No
create bdd to test header options	Not started	No
create the add staff fucntion to website	Not started	No
create new learning material form	Not started	No
create new previous project form	Not started	No
create new project form	Not started	No
extra projoct data to website	Not started	No
extract previous project from database	Not started	No
extract saved learing material form database	Not started	No
create edit and delete learing material	Not started	No
create edit and delete project	Not started	No
create edit staff	Not started	No
create email checker	Not started	No
create function to allow certain staff to edit content	Not started	No
create the fillitering options for the projects	Not started	No
create the response featue of the project	Not started	No
add validation to new users	Not started	No
add validation to previous project	Not started	No
add validation to project	Not started	No
develop some accessibility	Not started	No
research content for website through questionnaires	Not started	No
create seed for learning section	Not started	No
gather learning advice	Not started	No
carry out desk resrearch	Not started	No
design high fidleity	Not started	No
design low fidelity	Not started	No
carry out focus group for designs	Not started	No
create front end look	Not started	No
gather project and previous project resource	Not started	No
image optimisation	Not started	No
add content to website	Not started	No
carry out cognitive walkthrough of the website	Not started	No